## afrohr-brand-serp-30day-tracker
Day | Week | Task | Done | Owner | Date Completed | Notes | Observed Impact
1 | 1 | Standardize brand text everywhere to AfroHR (site title, footer, social bios, contact blocks).
2 | 1 | Validate homepage schema in Rich Results Test and resolve warnings/errors.
3 | 1 | Verify Organization fields (name, logo, url, sameAs, contactPoint).
4 | 1 | Audit canonicals for key routes (home, login, dashboard, jobs).
5 | 1 | Submit sitemap in Search Console and request homepage indexing.
6 | 1 | Verify robots/indexability for all core pages.
7 | 1 | Capture baseline metrics (impressions, CTR, indexed pages, referring domains).
8 | 2 | Optimize Instagram profile identity and website link consistency.
9 | 2 | Optimize Facebook profile identity and website link consistency.
10 | 2 | Optimize YouTube channel branding/About and website link.
11 | 2 | Add AfroHR in 3 high-quality business directories.
12 | 2 | Add AfroHR in 3 more high-quality directories.
13 | 2 | Secure 1 external mention/backlink from relevant source.
14 | 2 | Audit all citations for exact identity consistency (name/logo/url/contact).
15 | 3 | Improve About page depth (mission, trust, timeline, leadership).
16 | 3 | Improve Contact page clarity (channels, support, response expectations).
17 | 3 | Publish/refresh Team or Leadership page.
18 | 3 | Publish branded article: What is AfroHR.
19 | 3 | Publish intent article: AfroHR for Employers/Candidates.
20 | 3 | Strengthen homepage internal links to key brand pages.
21 | 3 | Request indexing for all updated/published pages.
22 | 4 | Run branded search demand campaign post #1.
23 | 4 | Run branded search demand campaign post #2.
24 | 4 | Optimize homepage title/meta for stronger branded CTR.
25 | 4 | Optimize About page title/meta.
26 | 4 | Optimize Contact page title/meta.
27 | 4 | Analyze Search Console for brand query variants and clicks.
28 | 4 | Compare metrics vs Week 1 baseline and log movement.
29 | 4 | Document wins, misses, and blockers.
30 | 4 | Define next 30-day sprint using top-performing actions.
KPI | Baseline (W1D7) | Week 2 | Week 3 | Week 4 | Target Trend
Branded Impressions (Search Console) |  |  |  |  | Up
Branded CTR (%) |  |  |  |  | Up
Branded Clicks |  |  |  |  | Up
Indexed Core Pages (count) |  |  |  |  | Up
Referring Domains (count) |  |  |  |  | Up
Structured Data Errors (count) |  |  |  |  | Down
Structured Data Warnings (count) |  |  |  |  | Down
Sitelinks present on branded query (Y/N) |  |  |  |  | Yes